## 2009
Annual complex procurement program of Konakovskaya GRES branch for 2009
Approved by the resolution of the Board of Directors, Minutes No. 8 dated of 24.04.2009
Item No. | Unit/enterprise- products consumer | Purchase order number | Lot number | Lot description | Planned Procurement method | Time Interval (*) of official declaration on commencement of procedures | Financial source | The year of commencement of delivery of goods, work performance, providing of services | The month of commencement of delivery of goods, work performance, providing of services | The year of the end of deliveries of goods, work performance, providing of services | The month of the end of deliveries of goods, work performance, providing of services | Procurement Management
| 1st group | Third group | Fourth group | Fifth group | Sixth group | Seventh group | Eighth group | Tenth group | 11th group | 12th group | 13th group | 14th group
1. Fuel for power plants
1 | KGRES branch | 1 | 1 | Gas NOVATEK | Single Source | January | Net cost | 2009 | January | 2009 | June | OJSC OGK-5
2 | KGRES branch | 2 | 1 | Additional gas | Single Source | March | Net cost | 2009 | April | 2009 | December | OJSC OGK-5
3 | KGRES branch | 3 | 1 | Home heating oil М-100 | Open Tender | January | Net cost | 2009 | March | 2009 | September | OJSC OGK-5
2.1. Construction, modernization and re-equipment of power facilities (other investment outlay) - works
4 | KTS (boiler turbine shop) | 4 | 1 | Technical re-equipment of the power unit No. 5 | Open Request for Proposals | February | Amortization | 2009 | May | 2009 | October | OJSC OGK-5
5 | KTS (boiler turbine shop) | 5 | 1 | Technical re-equipment of Burning Management System of the power unit No. 5 | Open Tender | February | Amortization | 2009 | April | 2009 | October | OJSC OGK-5
6 | KTS (boiler turbine shop) | 6 | 1 | Technical re-equipment of GRP-1 (Gas Supply system) | Open Tender | February | Amortization | 2009 | April | 2009 | October | OJSC OGK-5
7 | TTS | 7 | 1 | Technical re-equipment of loading/unloading rack No.1 at mazut plant | Open Tender | March | Amortization | 2009 | April | 2009 | October | OJSC OGK-5
8 | KTS (boiler turbine shop) | 8 | 1 | Technical re-equipment of crane runways of smoke extractor section | Open Tender | March | Amortization | 2009 | May | 2009 | November | OJSC OGK-5
9 | ES | 9 | 1 | Technical re-equipment of mazut storage tank No.13 | Open Tender | February | Amortization | 2009 | March | 2009 | November | OJSC OGK-5
10 | SB | 10 | 1 | Guarding security of the station | Open Tender | February | Amortization | 2009 | February | 2009 | October | OJSC OGK-5
11 | ES | 11 | 1 | Appraisal of the project "Refurbishment of 500 kV outdoor switchgear (ORU)" | Single Source | March | Amortization | 2009 | April | 2009 | August | OJSC OGK-5
2.2. Construction, modernization and re-equipment of power facilities (other investment outlay) - equipment supply
12 | CTAI | 12 | 1 | Thermocouple and Resistance Thermometers manufactured by OJSC NPP Etalon | Open Request for Quotations | January | Amortization | 2009 | February | 2009 | April | OJSC OGK-5
13 | UIT | 13 | 1 | Fibre optic Welding Machine of type Fujikura FSM-17S, complete | Open Request for Quotations | January | Amortization | 2009 | February | 2009 | March | OJSC OGK-5
14 | Chemical shop | 14 | 1 | Chemical control devices | Open Request for Proposals | April | Amortization | 2009 | June | 2009 | July | OJSC OGK-5
15 | ETs,HTs, LMiNK | 15 | 1 | Technical control devices | Open Request for Proposals | April | Amortization | 2009 | June | 2009 | July | OJSC OGK-5
16 | ES | 16 | 1 | Installation CYCLONE-B- | Open Request for Quotations | April | Amortization | 2009 | June | 2009 | July | OJSC OGK-5
17 | LMiNK | 17 | 1 | Nondestructive testing instrument UDTs-201P | Open Request for Quotations | April | Amortization | 2009 | June | 2009 | July | OJSC OGK-5
18 | ES | 18 | 1 | Portable Earth connections | Open Request for Quotations | April | Amortization | 2009 | June | 2009 | June | OJSC OGK-5
3.1. Power repair production - works
19 | KTS (boiler turbine shop) | 19 | 1 | After-sales service based on technical condition of turbines K-300-240 | Single Source para | February | Net cost | 2009 | April | 2009 | December | OJSC OGK-5
20 | Power plant-wide equipment | 20 | 1 | Routine repair of foundations. | Open Request for Proposals | January | Net cost | 2009 | March | 2009 | December | OJSC OGK-5
21 | Power plant-wide equipment | 21 | 1 | Current maintenance of buildings and facilities | Open Request for Proposals | March | Net cost | 2009 | April | 2009 | December | OJSC OGK-5
22 | KTS | 22 | 1 | Equipment cleaning | Open Request for Proposals | March | Net cost | 2009 | April | 2009 | December | OJSC OGK-5
23 | KTS, fuel & transp.unit, chem. plant | 23 | 1 | Thermal insulation maintenance | Open Request for Proposals | March | Net cost | 2009 | April | 2009 | December | OJSC OGK-5
24 | BTR | 24 | 1 | Equipment lining maintenance | Open Request for Proposals | March | Net cost | 2009 | April | 2009 | December | OJSC OGK-5
3.2. Power repair production - supply of materials and spare parts
25 | CTAI | 12 | 1 | Thermocouple and Resistance Thermometers manufactured by OJSC NPP Etalon | Open Request for Quotations | February | Net cost | 2009 | March | 2009 | April | OJSC OGK-5
26 | CTAI | 25 | 1 | Analyzers of "Atlant" type manufactured by LLC "Atreco" | Single Source | March | Net cost | 2009 | March | 2009 | April | OJSC OGK-5
27 | CTAI | 26 | 1 | Analyzers MAK, ADS manufactured by LLC NPF Energopromkomplekt | Single Source | March | Net cost | 2009 | April | 2009 | April | OJSC OGK-5
28 | CTAI | 27 | 1 | Pressure indicators manufactured by LLC NPP Elemer | Single Source | March | Net cost | 2009 | April | 2009 | April | OJSC OGK-5
29 | CTAI | 28 | 1 | Pressure indicators manufactured by CJSC PG Metran | Single Source | March | Net cost | 2009 | April | 2009 | April | OJSC OGK-5
30 | CTAI | 29 | 1 | Pressure indicators manufactured by Company "Yokogawa" | Open Request for Quotations | February | Net cost | 2009 | March | 2009 | April | OJSC OGK-5
31 | CTAI | 30 | 1 | Non-standard turbine measurement devices manufactured by CJSC Energopribor | Open Request for Proposals | February | Net cost | 2009 | March | 2009 | April | OJSC OGK-5
32 | CTAI | 31 | 1 | Thermocouple and Resistance Thermometers manufactured by LLC PK Tesey | Open Request for Quotations | February | Net cost | 2009 | March | 2009 | April | OJSC OGK-5
33 | CTAI | 32 | 1 | Electric devices MEO manufactured by ABS ZEiM Avtomatizatsia | Open Request for Quotations | February | Net cost | 2009 | March | 2009 | April | OJSC OGK-5
34 | UIT | 33 | 1 | Controllers "ASKVD" manufactured by LLC NPP "Vicont" | Open Request for Quotations | February | Net cost | 2009 | March | 2009 | April | OJSC OGK-5
35 | CTAI | 34 | 1 | Automation devices and units | Open Request for Quotations | February | Net cost | 2009 | March | 2009 | April | OJSC OGK-5
36 | CTAI | 35 | 1 | Level Instruments | Open Request for Quotations | February | Net cost | 2009 | March | 2009 | April | OJSC OGK-5
37 | CTAI (thermal instrumentation & control shop), Electrical shop | 36 | 1 | Pressure instruments manufactured by OJSC "Teplocontrol" | Open Request for Quotations | February | Net cost | 2009 | March | 2009 | April | OJSC OGK-5
38 | ES | 37 | 1 | Isolators | Open Request for Proposals | February | Net cost | 2009 | March | 2009 | March | OJSC OGK-5
39 | ETs,HTs, TTTs | 38 | 1 | Pump equipment | Open Request for Proposals | February | Net cost | 2009 | April | 2009 | June | OJSC OGK-5
40 | ETs CTAI, UIT | 39 | 1 | Cable products | Open Request for Proposals | February | Net cost | 2009 | March | 2009 | March | OJSC OGK-5
41 | CTAI | 40 | 1 | Electric Motors | Open Request for Proposals | February | Net cost | 2009 | March | 2009 | March | OJSC OGK-5
42 | ES | 41 | 1 | Automatic machine manufactured by OJSC "Silovye Mashiny" | Open Request for Proposals | February | Net cost | 2009 | April | 2009 | September | OJSC OGK-5
43 | KTTs, CTAI (thermal instrumentation & control shop), Electrical shop | 42 | 1 | Carbon steel pipes | Open Request for Quotations | January | Net cost | 2009 | February | 2009 | March | OJSC OGK-5
44 | Electric shop, CTAI | 43 | 1 | Circuit Breakers | Open Request for Quotations | February | Net cost | 2009 | March | 2009 | March | OJSC OGK-5
45 | All shops | 44 | 1 | Fabricated rubber products | Open Request for Quotations | March | Net cost | 2009 | March | 2009 | March | OJSC OGK-5
46 | UIT, CTAI | 45 | 1 | Spare parts for office equipment | Open Request for Quotations | March | Net cost | 2009 | March | 2009 | May | OJSC OGK-5
47 | Electric shop | 46 | 1 | Bus supports BBS-330-3 УХЛ1 | Open Request for Quotations | February | Net cost | 2009 | March | 2009 | March | OJSC OGK-5
48 | Electric shop | 47 | 1 | Electrical Transducers | Open Request for Proposals | February | Net cost | 2009 | March | 2009 | March | OJSC OGK-5
49 | CTAI, Electric shop, SOK, TTS, KTS | 48 | 1 | Wire | Open Request for Quotations | March | Net cost | 2009 | April | 2009 | June | OJSC OGK-5
50 | Electric shop | 49 | 1 | Spare parts for high voltage circuit breakers | Open Request for Quotations | March | Net cost | 2009 | April | 2009 | April | OJSC OGK-5
51 | TsOK | 50 | 1 | Parts of pipeline (pipe-bends, flanges) | Open Request for Quotations | April | Net cost | 2009 | June | 2009 | August | OJSC OGK-5
52 | TsOK | 51 | 1 | Parts of pipeline (cocks) | Open Request for Quotations | April | Net cost | 2009 | June | 2009 | August | OJSC OGK-5
53 | Electric shop | 52 | 1 | Units BMRZ | Open Request for Proposals | February | Net cost | 2009 | April | 2009 | April | OJSC OGK-5
54 | CTAI | 53 | 1 | Spare parts for video cubes | Single Source para | March | Net cost | 2009 | May | 2009 | May | OJSC OGK-5
55 | Electric shop | 54 | 1 | Relay products | Open Request for Proposals | March | Net cost | 2009 | April | 2009 | April | OJSC OGK-5
56 | Electric shop | 55 | 1 | Cable fittings | Open Request for Quotations | March | Net cost | 2009 | April | 2009 | April | OJSC OGK-5
57 | Electric shop, CTAI, UIT | 56 | 1 | Wires and cords | Open Request for Quotations | April | Net cost | 2009 | May | 2009 | May | OJSC OGK-5
3.3. Power repair production - supply of materials and spare parts (insurance stock)
58 | KTS (boiler turbine shop) | 57 | 1 | Carbon steel pipes | Open Request for Quotations | February | Net cost | 2009 | April | 2009 | April | OJSC OGK-5
59 | KTS | 58 | 1 | Electric drives | Open Request for Quotations | February | Net cost | 2009 | May | 2009 | May | OJSC OGK-5
4.1. Operating Expenditure - services
60 | CNIO | 59 | 1 | Execution of works on survey of heat insulation and setting of the power units No.6, 7 | Open Request for Proposals | February | Net cost | 2009 | February | 2009 | December | OJSC OGK-5
61 | KTS (boiler turbine shop) | 60 | 1 | Development of technical design of the scheme for chemical treatment of production deposits on internal surfaces of water-steam circuit of the direct flow boiler at Konakovskaya GRES | Open Request for Proposals | January | Net cost | 2009 | February | 2009 | September | OJSC OGK-5
62 | KTS (boiler turbine shop) | 61 | 1 | Technical diagnostics, inspection and expertise assessment of industrial safety of heating and mechanical equipment of Konakovskaya GRES branch after expiring of the assigned service life with purpose to prolong operating life thereof, development of recommendations on correction of detected defects. | Open Tender | March | Net cost | 2009 | May | 2009 | December | OJSC OGK-5
63 | ES | 62 | 1 | After-sale service of equipment of VCPA of the power units No. 1, 3, 6 | Open Request for Proposals | February | Net cost | 2009 | January | 2009 | December | OJSC OGK-5
64 | HS (chemical shop) | 63 | 1 | Receipt and transportation of radioactive wastes (hereinafter referred to as RAW), storage of RAW prior to processing and conditioning, processing and conditioning of RAW, long-term storage of RAW packages. | Single Source para | January | Net cost | 2009 | February | 2009 | December | OJSC OGK-5
65 | KTS (boiler turbine shop) | 64 |  | Execution of Expert diagnostics of hoisting equipment | Single Source para | January | Net cost | 2009 | January | 2009 | December | OJSC OGK-5
66 | KTS (boiler turbine shop) | 65 | 1 | Execution of works on technical diagnostic, examination and expert review of Industrial safety of bends of live steam lines and reheat lines, piping within the boundaries of boiler and turbine, feed pipeline and boiler headers at the power unit No.5 | Open Request for Proposals | March | Net cost | 2009 | April | 2009 | December | OJSC OGK-5
67 | KTS (boiler turbine shop) | 66 | 1 | Execution of works on equipment preservation to ensure protection thereof against parking corrosion | Open Request for Proposals | February | Net cost | 2009 | March | 2009 | December | OJSC OGK-5
68 | KTS (boiler turbine shop) | 67 | 1 | Planned maintenance of RZU at BNS-2 | Single Source para | February | Net cost | 2009 | March | 2009 | December | OJSC OGK-5
69 | KTS (boiler turbine shop) | 68 | 1 | The survey of the state of bricking gas ducts of the power unit No.5 | Open Request for Proposals | March | Net cost | 2009 | April | 2009 | August | OJSC OGK-5
70 | TTS | 69 | 1 | Diagnostics of process buildings and facilities of loading/unloading rack No.1, 2, 3 at mazut plant warehouse | Open Request for Proposals | February | Net cost | 2009 | April | 2009 | August | OJSC OGK-5
71 | TTS | 70 | 1 | Survey of equipment of TTS | Open Request for Proposals | March | Net cost | 2009 | April | 2009 | September | OJSC OGK-5
72 | TTS | 71 | 1 | Cleaning of boreholes of artesian wells No. 3,5,6,7,8,9 | Open Request for Proposals | February | Net cost | 2009 | April | 2009 | July | OJSC OGK-5
73 | KTS (boiler turbine shop) | 72 | 1 | Development of the program for calculation of efficiency of the K-300-240 turbine including diagnostics of CVD (high pressure cylinders) and CSD (medium pressure cylinders) | Single Source para | February | Net cost | 2009 | March | 2009 | December | OJSC OGK-5
74 | KTS (boiler turbine shop) | 73 | 1 | Development of automated system for technical diagnostics of heating surfaces of the PK-41 boiler | Single Source para | February | Net cost | 2009 | March | 2009 | December | OJSC OGK-5
75 | ES | 74 | 1 | Testing of stator of TG-4 of the power unit No.4 | Open Request for Proposals | March | Net cost | 2009 | May | 2009 | June | OJSC OGK-5
76 | ES | 75 | 1 | Application of fireproofing compound on cables of the power units No. 6-8 | Open Request for Proposals | February | Net cost | 2009 | March | 2009 | September | OJSC OGK-5
77 | ES | 76 | 1 | Complex diagnostic survey of packaged transformers Т-5А, Т-5Б, Т-8А | Open Request for Proposals | February | Net cost | 2009 | April | 2009 | December | OJSC OGK-5
78 | ES | 77 | 1 | Carrying out Industrial Safety Expertise for insulators of air circuit breakers :SVV-330, SHSV-500, VV-500 VL «Opytnaya». | Open Request for Proposals | March | Net cost | 2009 | April | 2009 | October | OJSC OGK-5
79 | ES | 78 | 1 | Routine maintenance of the territory of ORU (outdoor switchgear)-35;220;330;500 kV and OTP-220;500 kV. | Open Request for Proposals | April | Net cost | 2009 | June | 2009 | September | OJSC OGK-5
80 | PTO (Production Technology Department) | 79 | 1 | Receipt, transportation, processing and long term storage of ashes produced as a result of burning of sulphur mazuts | Single Source para | May | Net cost | 2009 | June | 2009 | November | OJSC OGK-5
81 | PTO (Production Technology Department) | 80 | 1 | Development of draft standards on maximum permissible discharges (MPD) of pollutants into water bodies | Open Request for Proposals | August | Net cost | 2009 | October | 2009 | December | OJSC OGK-5
82 | PTO (Production Technology Department) | 81 | 1 | Development of plans for emergency situations liquidation and localisation | Open Request for Proposals | April | Net cost | 2009 | June | 2009 | August | OJSC OGK-5
83 | TTS | 82 | 1 | Sanitary-engineering -sealing-off of artesian wells No.1,4 | Open Request for Proposals | June | Net cost | 2009 | August | 2009 | October | OJSC OGK-5
4.2. Operating Expenditure - supply of materials
84 | UIT, CTAI | 83 | 1 | Consumables for office equipment | Open Request for Quotations | January | Net cost | 2009 | February | 2009 | May | OJSC OGK-5
85 | HS (chemical shop) | 84 | 1 | Ion exchange resin АВ-17-8** as per GOST 20301-74 | Open Tender | January | Net cost | 2009 | March | 2009 | June | OJSC OGK-5
86 | HS (chemical shop) | 85 | 1 | Ion exchange resin KU-2-8** as per GOST 20298-74 | Open Tender | March | Net cost | 2009 | April | 2009 | June | OJSC OGK-5
87 | HS (chemical shop) | 86 | 1 | Ammonia water solution 25% as per GOST 9-92, technical grade B | Open Request for Quotations | March | Net cost | 2009 | April | 2009 | November | OJSC OGK-5
88 | HS (chemical shop) | 87 | 1 | Ion exchange resin Levatite EN 10204-3.1В МР-64 | Open Request for Proposals | March | Net cost | 2009 | April | 2009 | March | OJSC OGK-5
89 | СС, TTS | 88 | 1 | Diesel | Single Source para | January | Net cost | 2009 | January | 2009 | December | OJSC OGK-5
90 | UD | 89 | 1 | Mogas (including mogas АI-92, АI-95) | Single Source para | January | Net cost | 2009 | January | 2009 | December | OJSC OGK-5
91 | CTAI | 90 | 1 | Multimeters | Open Request for Quotations | March | Net cost | 2009 | April | 2009 | June | OJSC OGK-5
92 | Chemical shop | 91 | 1 | Coagulant Aluminum sulphate | Single Source para | February | Net cost | 2009 | March | 2009 | December | OJSC OGK-5
93 | UIT, CTAI | 92 | 1 | Office equipment | Open Request for Quotations | March | Net cost | 2009 | April | 2009 | April | OJSC OGK-5
94 | All subdivisions | 93 | 1 | Polygraphic items | Open Request for Proposals | February | Net cost | 2009 | March | 2009 | March | OJSC OGK-5
95 | HS (chemical shop) | 94 | 1 | Polyacrylamide gel technical as per TU 6-0201049-92 | Open Request for Quotations | March | Net cost | 2009 | April | 2009 | December | OJSC OGK-5
96 | All shops | 95 | 1 | Fuels and lubricants | Open Request for Quotations | March | Net cost | 2009 | April | 2009 | April | OJSC OGK-5
97 | TTS, CC, ETs | 96 | 1 | Transformer oil "GK" | Open Request for Quotations | March | Net cost | 2009 | April | 2009 | April | OJSC OGK-5
98 | All subdivisions | 97 | 1 | Work wear | Single Source para | March | Net cost | 2009 | April | 2009 | September | OJSC OGK-5
99 | КТS, HS, CTAI, ETs,COK, ТТS, SB, СС | 98 | 1 | Fire Fighting Equipment (fire-hose barrels, fire-hoses, fire cocks) | Open Request for Quotations | April | Net cost | 2009 | July | 2009 | August | OJSC OGK-5
100 | ТТS, HS | 99 | 1 | Activated carbon АBG | Open Request for Quotations | March | Net cost | 2009 | April | 2009 | April | OJSC OGK-5
101 | Electric shop | 100 | 1 | Electrical brushes for generator | Single Source para | February | Net cost | 2009 | March | 2009 | June | OJSC OGK-5
102 | CTAI | 101 | 1 | Set of Reagents "А-85.420.13 Silica Reagents" for silicic acid analyzer | Open Request for Quotations | March | Net cost | 2009 | April | 2009 | April | OJSC OGK-5
103 | ES, CTAI, COK | 102 | 1 | Electrical hand tools | Open Request for Quotations | March | Net cost | 2009 | April | 2009 | March | OJSC OGK-5
104 | ES, CTAI, COK | 103 | 1 | Tool | Open Request for Quotations | March | Net cost | 2009 | April | 2009 | March | OJSC OGK-5
105 | All subdivisions | 104 | 1 | Stationery | Open Request for Proposals | March | Net cost | 2009 | May | 2009 | November | OJSC OGK-5
106 | Electric shop, CTAI | 16 | 1 | Portable Earth connections | Open Request for Quotations | April | Net cost | 2009 | June | 2009 | June | OJSC OGK-5
107 | All subdivisions | 105 | 1 | Personnel Safety Equipment | Open Request for Proposals | April | Net cost | 2009 | June | 2009 | June | OJSC OGK-5
108 | KTS (boiler turbine shop) | 106 | 1 | Sealant Аг-4и as per TU 26-02-592-83 | Open Request for Quotations | May | Net cost | 2009 | July | 2009 | July | OJSC OGK-5
109 | Electrical shop | 107 | 1 | Heat-resistant packages | Single Source para | April | Net cost | 2009 | April | 2009 | April | OJSC OGK-5
110 | CTAI | 108 | 1 | Fanfold chart paper RP Regopen , Czech Republic | Open Request for Quotations | July | Net cost | 2009 | August | 2009 | August | OJSC OGK-5
111 | HS (chemical shop) | 109 | 1 | Sulphuric acid, technical grade 1as per GOST 2184-77 in the 1st quarter of 2009 | Restricted Request for Quotations based on results of Open Tender | January | Net cost | 2009 | February | 2009 | March | OJSC OGK-5
112 | HS (chemical shop) | 110 | 1 | Sulphuric acid, technical grade 1as per GOST 2184-77 in the 2nd quarter of 2009 2009 | Restricted Request for Quotations based on results of Open Tender | March | Net cost | 2009 | April | 2009 | June | OJSC OGK-5
113 | HS (chemical shop) | 111 | 1 | Sulphuric acid, technical grade 1as per GOST 2184-77 in the 3rd quarter of 2009 2009 | Restricted Request for Quotations based on results of Open Tender | June | Net cost | 2009 | July | 2009 | September | OJSC OGK-5
114 | HS (chemical shop) | 112 | 1 | Sulphuric acid, technical grade 1as per GOST 2184-77 in the 4th quarter of 2009 | Restricted Request for Quotations based on results of Open Tender | September | Net cost | 2009 | October | 2009 | December | OJSC OGK-5
5.1. Other procurement
115 | UIT | 113 | 1 | Communication and data transmission services | Single Source para | January | Net cost | 2009 | January | 2009 | December | OJSC OGK-5
116 | СС, TTS | 114 | 1 | Transportation services of С-З GP "Promzheldortrans" including routine maintenance of railways and turnouts, services related to feed and cleaning of railway carriages | Single Source para | January | Net cost | 2009 | January | 2009 | December | OJSC OGK-5
117 | GRES | 115 | 1 | advertising services | Single Source para | March | Net cost | 2009 | March | 2009 | December | OJSC OGK-5
118 | UD | 116 | 1 | Vehicle Maintenance | Single Source para | January | Net cost | 2009 | January | 2009 | December | OJSC OGK-5
119 | GRES | 117 | 1 | Subscription, NTD (scientific and technical documents), NTL (scientific and technical literature) | Single Source para | March | Net cost | 2009 | March | 2009 | December | OJSC OGK-5
120 | SNTB | 118 | 1 | Medical examination of personnel | Single Source para | March | Net cost | 2009 | April | 2009 | September | OJSC OGK-5