## ГКПЗ 2009
Annual complex procurement program of Nevinnomysskaya GRES branch for 2009
Approved by the resolution of the Board of Directors, Minutes No. 8 dated of 24.04.2009
Item No. | Unit - products consumer | Purchase order number | Lot number | Lot description | Planned Procurement method | Time Interval of official declaration on commencement of procedures | Financial source | The year of commencement of delivery of goods, work performance, providing of services | The month of commencement of delivery of goods, work performance, providing of services | The year of the end of deliveries of goods, work performance, providing of services | The month of he end of deliveries of goods, work performance, providing of services | Procurement Management
1st group | 2nd group | Third group | Fourth group | Fifth group | Sixth group | 7th group | 8th group | 10th group | 11th group | 12th group | 13th group | 14th group
1. Fuel for power plants
1 | NGRES branch | 1 | 1 | Gas NOVATEK | Single Source | January | Net cost | 2009 | January | 2009 | December | OJSC OGK-5
2 | NGRES branch | 2 | 1 | Transportation of gas | Single Source | January | Net cost | 2009 | January | 2009 | December | OJSC OGK-5
3 | NGRES branch | 3 | 1 | Fuel oil | Open tender | January | Net cost | 2009 | March | 2009 | September | OJSC OGK-5
2.1. Construction, modernization and re-equipment of power facilities (other investment outlay) - works
4 | STPR | 4 | 1 | Development of engineering documentation for technical upgrading of the steam pipe OP, SK crossover pipes of the boiler unit #2 | Open Request for Proposals | March | Depreciation | 2009 | May | 2009 | October | OJSC OGK-5
5 | STPR | 5 | 1 | CAW "Replacement of gantry crane with lifting capacity of 100/20 tonnes located above the KTS-1 machinery hall" | Open tender | July | Depreciation | 2009 | October | 2010 | July | OJSC OGK-5
6 | STPR | 6 | 1 | Refurbishment of fire alarm units | Open Request for Proposals | March | Depreciation | 2009 | May | 2009 | December | OJSC OGK-5
7 | STPR | 7 | 1 | Development of DD (Detailed Design) "Replacement of the 0.5 ton carrying capacity passenger lift at ABK " | Open Request for Proposals | September | Depreciation | 2009 | November | 2010 | May | OJSC OGK-5
8 | STPR | 8 | 1 | Development of DD (Detailed Design) "Replacement of overhead travelling cranes with lifting capacity of 30/5 tonnes (2 units) for boilers of KTS-1" | Open Request for Proposals | August | Depreciation | 2009 | November | 2010 | May | OJSC OGK-5
9 | STPR | 9 | 1 | Development of DD (Detailed Design) "Replacement of overhead travelling crane with lifting capacity of 10 tonnes of boilers of KTS-1" | Open Request for Proposals | September | Depreciation | 2009 | November | 2010 | May | OJSC OGK-5
10 | STPR | 10 | 1 | DD (Detailed Design) "Replacement of gantry crane with lifting capacity of 75/20 tonnes located at machinery hall of KTS-2" | Open Request for Proposals | August | Depreciation | 2009 | November | 2010 | May | OJSC OGK-5
11 | STPR | 11 | 1 | DD (Detailed Design) "Replacement of gantry crane with lifting capacity of 6.3 tonnes located at BVZ" | Open Request for Proposals | September | Depreciation | 2009 | November | 2010 | May | OJSC OGK-5
12 | STPR | 12 | 1 | Replacement of the 2 ton carrying capacity goods lift of the boiler of st.No. 11 of KTS-2 | Open tender | May | Depreciation | 2009 | September | 2010 | June | OJSC OGK-5
13 | STPR | 13 | 1 | Refurbishment of fuel supply system of the boiler unit of st.No. № 10 | Open tender | March | Depreciation | 2009 | May | 2009 | November | OJSC OGK-5
14 | STPR | 14 | 1 | Upgrading of the ТVV-165-2 generator of st. №12 | Open tender | April | Depreciation | 2009 | July | 2010 | December | OJSC OGK-5
15 | STPR | 15 | 1 | Complex of engineering/technical security means 7th start-up complex (Extra purchase) | Single Source | February | Depreciation | 2009 | March | 2009 | December | OJSC OGK-5
16 | STPR | 16 | 1 | CAW at the facility "Refurbishment of GRP-1A Gas Supply system " 1st start-up complex (extra purchase) | Single Source | February | Depreciation | 2009 | March | 2010 | April | OJSC OGK-5
17 | STPR | 17 | 1 | Development of PPR (Work Execution Plan) for execution of CAW at the facility "Replacement of overhead travelling crane with lifting capacity of 100/20 tonnes located above the KTS-1 machinery hall" | Open Request for Proposals | March | Depreciation | 2009 | April | 2009 | June | OJSC OGK-5
18 | STPR | 18 | 1 | Technical re-equipment of main equipment of the power unit of st. № 10. Restoration of rotating blades of TG of st No. 10 by EIL method | Single Source | March | Net cost | 2009 | June | 2009 | October | OJSC OGK-5
19 | STPR | 19 | 1 | Engineering of fish-protecting system at BVZ | Open Request for Proposals | August | Depreciation | 2009 | October | 2010 | April | OJSC OGK-5
20 | STPR | 20 | 1 | CAW (construction-assembly work) at the facility "Refurbishment of compressor station " | Open tender | January | Depreciation | 2009 | March | 2009 | November | OJSC OGK-5
21 | STPR | 21 | 1 | PIR (Design & Survey) "Refurbishment of the R-50-130/-1 turbo unit of st. No. 4 with auxiliary equipment and pipelines and Implementation of automated process control system (APCS)" | Open tender | March | income | 2009 | April | 2010 | June | OJSC OGK-5
22 | STPR | 22 | 1 | CAW "Technical re-equipment of main equipment of the power unit of st. № 10" | Open tender | January | income | 2009 | March | 2009 | October | OJSC OGK-5
2.2. Construction, modernization and re-equipment of power facilities (other investment outlay) - equipment supply
23 | ETL | 23 | 1 | Diagnostic facilities and devices Seba KMT | Open tender | January | Depreciation | 2009 | March | 2009 | March | OJSC OGK-5
24 | HS (chemical shop) | 24 | 1 | Laboratory devices | Open Request for Proposals | January | Depreciation | 2009 | April | 2009 | May | OJSC OGK-5
25 | OPPPR | 25 | 1 | 1.Convective Superheater (KPP) VD 2 st.with headers; 2.Convective Superheater (KPP) VD1 with headers of boiler ТGM-94. 3. Set of headers of inlet and outlet KPP ND 2 st. | Open Request for Proposals | January | Depreciation | 2009 | April | 2009 | April | OJSC OGK-5
26 | OPPPR | 26 | 1 | Packing packages RVP | Open tender | January | Depreciation | 2009 | April | 2009 | April | OJSC OGK-5
27 | OPPPR | 27 | 1 | Central seal RVVP-54 | Open Request for Proposals | March | Depreciation | 2009 | May | 2009 | June | OJSC OGK-5
28 | CTAI | 28 | 1 | Chemical control devices of type QUARTZ | Open Request for Quotations | January | Depreciation | 2009 | February | 2009 | March | OJSC OGK-5
29 | CTAI | 29 | 1 | Protective gas devices | Open Request for Quotations | January | Depreciation | 2009 | March | 2009 | March | OJSC OGK-5
30 | CTAI | 30 | 1 | Vibration control device ASKVD | Open tender | January | Depreciation | 2009 | April | 2009 | April | OJSC OGK-5
31 | ETL | 31 | 1 | Instruments for measurement of electrical parameters | Open Request for Proposals | February | Depreciation | 2009 | April | 2009 | June | OJSC OGK-5
32 | TsOK | 32 | 1 | Dynamometers | Open Request for Quotations | February | Depreciation | 2009 | May | 2009 | June | OJSC OGK-5
33 | NGRES | 33 | 1 | Ventilation systems and air conditioning units | Open Request for Proposals | February | Depreciation | 2009 | April | 2009 | May | OJSC OGK-5
34 | ETL | 34 | 1 | Portable combined installation for dielectrical diagnostics of cables | Open Request for Proposals | July | Depreciation | 2009 | November | 2009 | November | OJSC OGK-5
35 | NGRES | 35 | 1 | Laboratory instrument Mettler Toledo | Open Request for Quotations | March | Depreciation | 2009 | April | 2009 | April | OJSC OGK-5
36 | NGRES | 36 | 1 | Signalling indicators | Open Request for Quotations | March | Depreciation | 2009 | March | 2009 | March | OJSC OGK-5
37 | NGRES | 37 | 1 | Set of furniture for the conference room | Open Request for Quotations | March | Depreciation | 2009 | April | 2009 | June | NGRES
3.1. Power repair production - works
38 | SP (mid level repair) | 38 | 1 | Repair of heat insulation during mid-life repairs of the power unit of st. No. 9 and PGU-170 of st. №12,13. | Open tender | January | Net cost | 2009 | March | 2009 | July | OJSC OGK-5
39 | SP (mid level repair) | 39 | 1 | Repair of setting during mid-life repairs of the power unit of st. No. 9 and PGU-170 of st. №12,13. | Open tender | January | Net cost | 2009 | March | 2009 | July | OJSC OGK-5
40 | Boiler turbine shop KTS-2 | 40 | 1 | Supervision works on overhaul of Transformer T-10 | Single Source | March | Net cost | 2009 | June | 2009 | October | OJSC OGK-5
41 | SP (mid level repair) | 41 | 1 | Thermal insulation maintenance during the periods of the current maintenance and maintenance according to the technical condition of the main and auxiliary equipment of NGRES | Open Request for Proposals | March | Net cost | 2009 | April | 2009 | December | OJSC OGK-5
42 | SP (mid level repair) | 42 | 1 | Boiler cleaning works during the periods of the current maintenance and maintenance according to the technical condition of the main and auxiliary equipment of NGRES | Open Request for Proposals | March | Net cost | 2009 | April | 2009 | December | OJSC OGK-5
43 | SP (mid level repair) | 43 | 1 | Lining maintenance during the periods of the current maintenance and maintenance according to the technical condition of the main and auxiliary equipment of NGRES | Open Request for Proposals | March | Net cost | 2009 | April | 2009 | December | OJSC OGK-5
3.2. Power repair production - supply of materials and spare parts
44 | OPPPR | 44 | 1 | Central seal RVVP-54 | Open Request for Proposals | March | Net cost | 2009 | May | 2009 | June | OJSC OGK-5
45 | CTAI | 45 | 1 | Chemical control devices of type QUARTZ | Open Request for Quotations | January | Net cost | 2009 | February | 2009 | March | OJSC OGK-5
46 | CTAI | 46 | 1 | Chemical control devices of type GAMMA | Open Request for Quotations | January | Net cost | 2009 | February | 2009 | March | OJSC OGK-5
47 | CTAI | 47 | 1 | Protective gas devices | Open Request for Quotations | January | Net cost | 2009 | March | 2009 | March | OJSC OGK-5
48 | CTAI | 48 | 1 | Vibration control devices | Open Request for Quotations | February | Net cost | 2009 | March | 2009 | March | OJSC OGK-5
49 | CTAI | 49 | 1 | Breakdown recorder AURA | Open Request for Quotations | March | Net cost | 2009 | May | 2009 | June | OJSC OGK-5
50 | CTAI | 50 | 1 | Signalling indicators | Open Request for Quotations | March | Net cost | 2009 | March | 2009 | March | OJSC OGK-5
51 | ETL | 51 | 1 | Device BSSDZ-01/02 | Single Source | March | Net cost | 2009 | June | 2009 | June | OJSC OGK-5
3.3. Power repair production - supply of materials and spare parts (insurance stock)
52 | OPPPR | 52 | 1 | Impulse Valve 586-20-ЭМ-02 | Open Request for Proposals | March | Net cost | 2009 | May | 2009 | May | OJSC OGK-5
4.1. Operating Expenditure - services
53 | TsOK | 53 | 1 | Technical diagnostic of hoisting cranes which have exhausted their rated service life. | Open Request for Proposals | January | Net cost | 2009 | January | 2009 | February | OJSC OGK-5
54 | TsOK | 54 | 1 | Complex survey of cranes runways | Open Request for Proposals | January | Net cost | 2009 | March | 2009 | April | OJSC OGK-5
55 | LMNK | 55 | 1 | Survey of the state of metal and extending service life of the frame of boiler ТGМ-94 st.No.10 and ТP-15 of st. No.3а | Open Request for Proposals | January | Net cost | 2009 | January | 2009 | October | OJSC OGK-5
56 | PTO (Production Technology Department) | 56 | 1 | Complex technical survey of power-machinery fuel oils | Open Request for Proposals | January | Net cost | 2009 | February | 2009 | December | OJSC OGK-5
57 | Chemical shop | 57 | 1 | Complex technical survey of the building of central chemical laboratory | Open Request for Proposals | February | Net cost | 2009 | May | 2009 | July | OJSC OGK-5
58 | Chemical shop | 58 | 1 | Correction of Technical Passports of process buildings and structures | Open Request for Proposals | March | Net cost | 2009 | June | 2009 | October | OJSC OGK-5
59 | Chemical shop | 59 | 1 | Complex technical survey of buildings for chemical water treatment and condensate treatment. | Open Request for Proposals | March | Net cost | 2009 | June | 2009 | August | OJSC OGK-5
60 | TsOK | 60 | 2 | Complex technical survey of the building of sanitary technicians shop | Open Request for Proposals | March | Net cost | 2009 | June | 2009 | July | OJSC OGK-5
61 | Boiler turbine shop KTS-1 | 61 | 1 | Complex technical survey of the building of the Fire Pumping Station of KTS-1 | Open Request for Proposals | April | Net cost | 2009 | July | 2009 | August | OJSC OGK-5
62 | Chemical shop | 62 | 2 | Complex technical survey of building structures of Clarifiers of OBHVO (water treatment plant) | Open Request for Proposals | April | Net cost | 2009 | July | 2009 | September | OJSC OGK-5
63 | TTS | 63 | 1 | Complex technical survey of foundations and earth bunds of the mazut storage tanks No. 1, 2, 3 of mazut plant No. 2 of the Nevinnomysskaya GRES branch of OJSC OGK-5. | Open Request for Proposals | May | Net cost | 2009 | August | 2009 | October | OJSC OGK-5
64 | Chemical shop | 64 | 1 | Complex technical survey of foundations of supports of slurry pipes at chemical shop | Open Request for Proposals | May | Net cost | 2009 | August | 2009 | October | OJSC OGK-5
65 | STPR | 65 | 1 | Execution of the topographic survey of the following facilities: 1. Power cable and control cable route from ORU-330 kV to main production site of the station. 2. GRP-1А. 3. Territories of slurry pipes and sludge reservoirs | Single Source | March | Net cost | 2009 | April | 2009 | April | OJSC OGK-5
66 | ES | 66 | 1 | Complex survey of the technical state of turbo generator G-10 | Open Request for Proposals | April | Net cost | 2009 | June | 2009 | July | OJSC OGK-5
67 | ES | 67 | 1 | Heat testing of G-1 | Open Request for Proposals | September | Net cost | 2009 | November | 2010 | January | OJSC OGK-5
68 | ES | 68 | 1 | Hook Up of multichannel video graphical recording transducers Ш9329 АИ (type 29.013) | Open Request for Proposals | June | Net cost | 2009 | August | 2009 | October | OJSC OGK-5
69 | LMNK | 69 | 1 | Survey of the state of metal and extending service life of steam pipeline of GPP and outlet headers of stage 1 of low pressure Superheater of the power unit of st. No. 10 at Nevinnomysskaya GRES branch | Open Request for Proposals | May | Net cost | 2009 | July | 2009 | September | OJSC OGK-5
70 | Boiler turbine shop KTS-2 | 70 | 1 | Instrumental survey of mechanical equipment of GTS in order to determine remaining life thereof. | Open Request for Proposals | March | Net cost | 2009 | April | 2009 | November | OJSC OGK-5
71 | TsOK | 71 | 1 | Hydromechanical washing of internal surface of pipelines of storm and faecal sewers at the territory of NGRES branch | Open Request for Proposals | April | Net cost | 2009 | June | 2009 | September | OJSC OGK-5
72 | TsOK | 72 | 1 | Maintenance of compressors Direct-280, Variable-260 | Open Request for Proposals | August | Net cost | 2009 | October | 2009 | December | OJSC OGK-5
73 | CTAI | 73 | 1 | Analysis of the electromagnetic situation of control and monitoring devices of the power units of st. No.10 and st. No. 11 in order to design scheme of organized earthing and to issue recommendations on protection against static electricity | Open Request for Proposals | February | Net cost | 2009 | April | 2009 | December | OJSC OGK-5
74 | Boiler turbine shop KTS-1 | 74 | 1 | Operating adjustment of installation ПТ-30/35-90/10-5М of st. № 1 | Open Request for Proposals | March | Net cost | 2009 | May | 2009 | October | OJSC OGK-5
75 | PTO (Production Technology Department) | 75 | 1 | Correcting of rated characteristics of a part of Heat and Power Plant after putting into operation TG of st. No. 1 PТ-30/35-90 | Open Request for Proposals | April | Net cost | 2009 | June | 2009 | November | OJSC OGK-5
4.2. Operating Expenditure - supply of materials
76 | NGRES | 76 | 1 | Special work clothing | Single Source | January | Net cost | 2009 | April | 2009 | December | OJSC OGK-5
77 | NGRES | 77 | 1 | Personnel Safety Equipment | Open Request for Proposals | February | Net cost | 2009 | April | 2009 | December | OJSC OGK-5
78 | TsOK | 78 | 1 | Turbine oil ТП-22С | Open Request for Proposals | March | Net cost | 2009 | June | 2009 | June | OJSC OGK-5 | 4788.5479 | -1822.5529 | multiplicity of supplies
79 | TsOK | 79 | 1 | Transformer oil "GK" | Open Request for Proposals | April | Net cost | 2009 | June | 2009 | June | OJSC OGK-5
80 | HS (chemical shop) | 80 | 1 | Aluminum sulphate, technical grade | Open Request for Quotations | August | Net cost | 2009 | October | 2009 | December | OJSC OGK-5 |  | -540 | Inventories
81 | HS (chemical shop) | 81 | 1 | Building lime | Open Request for Quotations | August | Net cost | 2009 | October | 2009 | December | OJSC OGK-5 |  | -61.875 | multiplicity of supplies | 275.625 | price averaging-out
82 | NGRES | 82 | 1 | Protective suits against electric arc | Single Source | February | Net cost | 2009 | May | 2009 | December | OJSC OGK-5
83 | NGRES | 83 | 1 | Activated charcoal | Open Request for Quotations | February | Net cost | 2009 | February | 2009 | March | OJSC OGK-5
84 | HS (chemical shop) | 84 | 1 | Activated charcoal | Open Request for Quotations | April | Net cost | 2009 | August | 2009 | August | OJSC OGK-5
85 | HS (chemical shop) | 85 | 1 | Sulphuric acid, technical grade | Restricted Request for Quotations based on results of open tender | April | Net cost | 2009 | April | 2009 | June | OJSC OGK-5
86 | HS (chemical shop) | 86 | 1 | Sulphuric acid, technical grade | Restricted Request for Quotations based on results of open tender | July | Net cost | 2009 | September | 2009 | September | OJSC OGK-5
87 | HS (chemical shop) | 87 | 1 | Sulphuric acid, technical grade | Restricted Request for Quotations based on results of open tender | August | Net cost | 2009 | October | 2009 | December | OJSC OGK-5
5.1. Other procurement
88 | Administrative Office (AHO) | 88 | 1 | Providing transport services | Single Source | January | Net cost | 2009 | January | 2009 | December | OJSC OGK-5
89 | PTO (Production Technology Department) | 89 | 1 | Development of the program for calculation of air emissions of pollutants from boiler units | Open Request for Proposals | January | Net cost | 2009 | February | 2009 | May | OJSC OGK-5
90 | PTO (Production Technology Department) | 90 | 1 | Development of "Draft standards on maximum permissible discharges of pollutants and microorganisms into water bodies for water consumer" | Open Request for Proposals | January | Net cost | 2009 | February | 2009 | June | OJSC OGK-5
91 | PTO (Production Technology Department) | 91 | 1 | Development and agreeing of "Draft standards on waste production and limits of its disposal " | Open Request for Proposals | March | Net cost | 2009 | May | 2009 | November | OJSC OGK-5
92 | PTO (Production Technology Department) | 92 | 1 | Development and agreeing of "Draft standards on maximum permissible air emissions (MPE) of pollutants" | Open Request for Proposals | April | Net cost | 2009 | June | 2009 | November | OJSC OGK-5
93 | NGRES | 93 | 1 | Upgrading Consultant Plus. | Single Source | January | Net cost | 2009 | February | 2010 | February | OJSC OGK-5
94 | NGRES | 94 | 1 | Technical support and upgrading of software RSDU-2 | Single Source | January | Net cost | 2009 | February | 2010 | February | OJSC OGK-5
95 | NGRES | 95 | 1 | Computers and office equipment | Open Request for Proposals | February | Net cost | 2009 | April | 2009 | May | OJSC OGK-5
96 | NGRES | 96 | 1 | Furniture | Open Request for Quotations | March | Net cost | 2009 | May | 2009 | December | NGRES
97 | NGRES | 97 | 1 | Providing of additional medical services ( Conducting routine Medical Fitness Examinations) | Open Request for Proposals | July | Net cost | 2009 | October | 2009 | October | NGRES
98 | NGRES | 98 | 1 | Safety Signs | Open Request for Quotations | March | Net cost | 2009 | May | 2009 | December | NGRES
99 | NGRES | 99 | 1 | Subscription to newspapers and magazines for the 2nd half year of 2009 | Single Source | May | Net cost | 2009 | July | 2009 | December | OJSC OGK-5
100 | NGRES | 100 | 1 | Subscription to newspapers and magazines for the 1st half year of 2010 | Single Source | September | Net cost | 2010 | January | 2010 | June | OJSC OGK-5
101 | NGRES | 101 | 1 | Spares for office equipment | Open Request for Proposals | February | Net cost | 2009 | March | 2009 | December | NGRES
102 | NGRES | 102 | 1 | Consumables for ACS | Open Request for Proposals | February | Net cost | 2009 | March | 2009 | December | NGRES